Statement of Work

OLR Control Room — ExxonMobil

Operational Learning Rate Platform on Microsoft Azure

EX3-compliant structure — 19 required sections, Agile fixed-capacity / variable-scope engagement model, Microsoft Paper.

1 · Document Control

| Attribute | Value |
| --- | --- |
| Project / Program Name | OLR Control Room — Operational Learning Rate Platform |
| Customer | Exxon Mobil Corporation ("Customer") |
| Prepared For | Senior Vice President, Global Operations (Sponsor) |
| Provider | Microsoft Corporation — Industry Solutions Delivery ("Microsoft ISD") |
| SOW Number | ISD-XOM-OLR-001 |
| Version | 1.1 — Amended (CR-02, CR-11, CR-14 incorporated; CR-01 N/A) |
| Date | [TBD on signature] |
| Status | Draft pending Customer and Microsoft signature |
| Work Order Reference | [TBD — to be assigned against the MCSA] |
| Validity | This SOW is valid for signature for 60 days from the Date above |
| Master Agreement | Microsoft Consulting Services Agreement (MCSA) — [reference TBD] |

2 · Introduction

2.1 Context

ExxonMobil is operating under five pressures identified during discovery: the Capital Triple-Lock (volume, returns, and emissions), the need to double the Pioneer synergy run-rate, a declining Low-Carbon Wallet trajectory, methane attribution across operated and non-operated assets, and a worsening process-safety trend. The Operational Learning Rate (OLR) approach — credited with $15.6B in structural savings since 2019 — now needs to scale across the integrated Pioneer estate while maintaining Operational Technology (OT) sovereignty.

This engagement aligns to ExxonMobil's strategic initiative to industrialize operational learning at scale through a governed, AI-enabled platform on Microsoft Azure.

2.2 Purpose of Engagement

Microsoft ISD will partner with ExxonMobil to design, build, harden, and transition into ExxonMobil operations an operable OLR Control Room: a governed Azure platform that synthesizes subsurface, drilling, completions, reliability, and methane signals into an engineer-facing AI advisor and an executive decision pack — without ever writing to plant control systems.

The collaboration is a joint delivery: Microsoft authors architecture, builds the platform, and transfers operational ownership; ExxonMobil owns outcomes, decisions, backlog priority, and operations after hypercare exit.

2.3 Engagement Model

Methodology: Agile Scrum, fixed-capacity / variable-scope.

Capacity: ~14,500 hours across 18 months (see §6 and §7).

Scope governance: Customer Product Owner prioritizes the backlog; Microsoft delivers within the agreed capacity envelope.

Structure: Single program with paired pods (Platform, Data, AI, Edge/OT, Security, Reliability), one governance layer (Product Council), and one executive steering committee.

The reference architecture, all nine Architecture Decision Records (ADRs), the 28-component system view, the Bill of Materials (BOM, 37 rows), the Work Breakdown Structure (WBS, 60 leaves), the 17 Non-Functional Requirements (NFR-01..17), the 7 Service Level Objectives (SLO-01..07), the 5 OT-boundary detection controls (DET-01..05), the 8 outcomes (O1..O8), the risk register, and the hostile-probe console are reflected in the OLR Control Room reference site and captured for this SOW in the executed PDF snapshot attached as Schedule H. The executed PDF snapshot is the authoritative technical baseline for this SOW. If this SOW and the Schedule H snapshot disagree, the Schedule H snapshot prevails on technical content and this SOW prevails on commercial and contractual terms. The live site is reference material only and does not expand or reduce scope unless changed through §12.

Defined terms and acronyms used throughout this SOW are catalogued in Schedule G — Glossary and Acronyms (§22).

3 · Objectives and Scope

3.1 Business Objectives

The engagement guides delivery toward the eight customer-owned outcomes published on the OLR site Traceability tab. Under the amended scope (CR-02, CR-11, CR-14), Microsoft is funded to deliver outcomes attributable to Pressure P1 — Volume-Returns-Emissions Triple Lock — via the OLR mechanism. The headline three:

Sustain earnings growth to 2030 by industrializing the OLR mechanism that produced $15.6B in structural savings since 2019 (Outcome O1 Earnings growth to 2030).

Transfer the operational learning rate onto Pioneer tier-2/tier-3 acreage, measured by per-well cycle-time and cost gap closure (Outcome O3 Production volume, O4 Structural cost reduction).

Establish a single semantic layer over operations, subsurface, and finance so the daily ops review and quarterly capital call read from the same signal (Outcome O5 Return on capital employed).

In-scope outcomes under this amendment: O1, O3, O4, O5 (P1-attributable). The remaining outcomes — O2 Cash-flow growth, O6 Capital returns, O7 Emissions performance, O8 Safety — remain referenced on the OLR site for traceability but are not contracted outcomes under this SOW; safety and emissions appear here only as assurance constraints (NFR-10 OT boundary, NFR-12 audit completeness), not as value-delivery commitments. See §5 (Out of Scope) and §12.4 (Change Order Log).

Non-guarantee clause. These objectives guide planning and prioritisation but are not contractually guaranteed within the capacity envelope. Realisation depends on Customer prioritisation of the backlog, data availability, third-party readiness, and operational adoption — see §10 (Risk), §18 (Customer Responsibilities), and §19 (Assumptions).

3.2 Value Themes

The engagement aligns to the following value themes, normalised across the platform:

Platform enablement — landing zone, identity, network, policy.

Application consolidation / delivery — engineer surface, executive surface.

Data & AI enablement — OSDU + ADX + Fabric semantic layer; Foundry RAG + Azure ML forecasting + safety graph.

Security & governance — Defender for Cloud, Sentinel, Content Safety, FinOps.

Migration / modernisation — historian read adapter, on-prem-to-cloud signal flow.

Operational efficiency — RUN-01..08 runbooks, error-budget policy, hypercare transition.

3.3 Scope Model

Scope is variable, governed by backlog prioritisation.

Delivery is capacity-driven: 14,500 hours over 18 months across MVP, GA, and Hypercare.

Customer Product Owner prioritises the backlog (a delegate of the Sponsor).

Microsoft ISD delivers within capacity and is accountable for technical quality, defensibility, and operational readiness against the hypercare exit gate (§17 / DEL-17).

4 · Structured Scope — Epics / Workstreams

4.1 Epic Categories

| Epic | Coverage | Reference |
| --- | --- | --- |
| E1 · Foundation / Baseline / Intake | Discovery validation, charter, ECIF approvals, reservations, mobilisation | OLR Mobilize |
| E2 · Architecture & Platform | Landing zone (hub-spoke + ExpressRoute Texas primary), AKS + Karpenter, AIO at edge | ADR-01, ADR-02, ADR-03 |
| E3 · Security & Identity | Entra ID identity boundary, Key Vault + HSM, Defender for Cloud, Sentinel, STRIDE-lite, OIMS coordination | ADR-01 |
| E4 · Data Plane Build | OSDU + ADX + Fabric three-tier; canonical event contract (Event Hubs + Event Grid + Service Bus); historian read adapter (one-way diode) | ADR-04, ADR-05, ADR-09 |
| E5 · AI Plane Build | Foundry RAG advisor, Azure ML forecasting, AI Search, Cosmos Gremlin safety graph, Content Safety | ADR-08 |
| E6 · Consumer Surfaces | Front Door, Managed Grafana (engineer), Power BI Premium (executive) | C-04, C-22, C-25 |
| E7 · Resilience & Governance | Active/Standby SCUS + NCUS, Monitor + LA, FinOps Hub on Fabric | ADR-06, ADR-07 |
| E8 · Scale / Expansion Waves | Site-by-site rollout from pilot pad to additional Pioneer-acreage sites | Deliver tab waves |
| E9 · Knowledge Transfer | Two-deep coverage, RUN-01..08 runbooks, hypercare transition | DEL-15, DEL-16 |

4.2 Scope Characteristics

Scope is non-fixed; the backlog is continuously reprioritised.

The backlog (60 leaf items in the OLR Control Room Deliver tab) drives sprint execution sequence and delivery cadence.

Material additions trigger §12 (Change Management).

5 · Out of Scope

The following items are explicitly excluded under this SOW:

Closed-loop OT control. Per ADR-09, any write path from the platform to Distributed Control Systems (DCS), Supervisory Control and Data Acquisition (SCADA), or Safety Instrumented Systems (SIS) is excluded for the duration of this SOW. Reversal requires a separate engagement, OIMS attestation, vendor certification, and ExxonMobil board approval.

Refining and chemicals plant integrations beyond the named upstream sites in the pilot wave.

Net-zero Plan / Low-Carbon Wallet decision support and methane attribution. Methane attribution, including operated-asset boundary attribution, and related ESG decision-support content are excluded under this SOW (SCP-OUT-02).

Microsoft 365 / Copilot for M365 deployment, end-user identity governance beyond platform consumers, and corporate-IT migrations.

Existing historian data migration or back-fill beyond read-side adapter configuration.

Third-party software licences and subscriptions (Customer-procured): PI / AVEVA, OSDU vendor, AOAI PTU reservations, Fabric F64 capacity, Power BI Premium.

Hardware and on-premises infrastructure provisioning at well-pad or OT perimeter network sites.

Organisational change management, end-user training, and communications outside the named technical role groups in §8.

24×7 ongoing managed operations post-hypercare. Microsoft remains available under separate Support agreements.

Performance testing of production OT systems — Customer-owned.

Amendment carve-outs (per §12.4 Change Order Log):

Process-safety value delivery (P5). Cosmos Gremlin safety graph, PSE precursor classifier, and safety-graph engineer-surface alerting (formerly D-08) are deferred / out of scope under this SOW. Safety remains an assurance constraint via NFR-10 (OT boundary integrity) and the five DET-01..05 controls; it is not a contracted value outcome.

Methane attribution and ESG reporting (P4). Operated-asset methane attribution semantic model and ESG decision-pack content (formerly D-09) are deferred / out of scope. Regulatory-shift narrative overlay (RSK-REG-01 mitigation) is removed from this SOW.

Pioneer-specific carve-out work (P2). The Pioneer-synergy-specific data products, MV resolution work (RSK-WORK-04, WBS 6.1/6.2), and second-acquisition data plane integrations are deferred. P1-attributable OLR transfer onto Pioneer acreage at the four named sites (CR-02) remains in scope.

Low-Carbon Wallet decision support (P3). Already out of scope under item 3 above; re-affirmed.

6 · Delivery Approach

6.1 Methodology

Agile Scrum is the primary delivery model. The engagement runs on a fixed-capacity, variable-scope basis. The Customer Product Owner prioritises the backlog; Microsoft delivers the top-priority items within the agreed capacity per sprint.

6.2 Core Mechanics

Product backlog: the central artifact, derived from the WBS in the OLR Control Room Deliver tab.

Sprint cycles: 2-week sprints; cadence agreed at Mobilize.

Iterative delivery with continuous reprioritisation.

Definition of Done: acceptance criteria per §9 satisfied, evidence linked on the proof graph.

6.3 Delivery Phases

| Phase | Purpose |
| --- | --- |
| Initiation (Mobilize) | Charter, governance, reservations, ECIF approvals, security model pre-circulation |
| Baseline Planning | Backlog grooming, capacity allocation, sprint zero |
| Delivery Sprints — MVP | Build core platform, pilot OT ingest, MVP advisor, MVP surfaces |
| Delivery Sprints — GA | Harden, integrate, validate DR, security attestation, runbook execution |
| Hypercare | Operational transition, exit-gate evidence, signed handoff |
| Closure | DEL-17 sign-off, retrospective, knowledge artifact handover |

7 · Timeline and Capacity Model

| Phase | Duration | Capacity (hrs) | Exit Gate |
| --- | --- | --- | --- |
| Mobilize (Initiation + Baseline) | T+0 → T+3 | ~700 (ECIF-absorbed) | Charter signed; reservations placed |
| MVP Build | T+3 → T+6 | 5,400 | DEL-04..08 green at first site |
| GA Hardening + Site Rollout (4 sites) | T+6 → T+12 | 7,200 | DEL-09..14 green; 4-site go-live |
| Hypercare & Transition | T+12 → T+18 | 1,900 | HG-01..06 attested across 4 sites; DEL-17 signed |
| Total contracted capacity (revised under CR-11) | 18 months | 14,500 | Prior cap 11,280 → raised to absorb CR-02 (4 sites) |

Timeline is relative, not a fixed commitment. It adapts to backlog priority and capacity consumption per §6. Capacity drivers under the amended scope: 1 customer pressure (P1) with OLR as the named mechanism, 28 components, 9 ADRs, 2 environments (SCUS primary + NCUS standby), and 4 sites in scope (CR-02) — 1 pilot at MVP followed by 3 additional sites rolled in across GA. The +3,220 hours over the original cap reflect site-specific rollout work (AIO onboarding, OT-DMZ provisioning, historian adapter, hypercare per site); platform-build hours are largely unchanged from v1.0.

8 · Organization and Roles

8.1 Structural Model

Executive Steering Committee — XOM Sponsor (Senior President Global Operations) + ISD CTO.

Product Council (Governance Layer) — XOM Product Owner, XOM Enterprise Architecture (Hansen, Kolesar), XOM OIMS lead, Microsoft Engagement Lead, Microsoft Solution Architect.

Delivery pods (Feature Teams) — Platform, Data, AI, Edge/OT, Security, Reliability — paired with XOM counterparts (two-deep).

8.2 Roles

Customer roles

| Role | Responsibility |
| --- | --- |
| Executive Sponsor | Outcomes, escalation, DEL-17 signature |
| Product Owner | Backlog priority, decision authority on sprint scope |
| Enterprise Architects (Hansen, Kolesar) | ADR co-ratification, design authority |
| OIMS / Cyber lead | ADR-09 attestation, security model approval |
| SMEs / Business stakeholders | Drilling, completions, reliability, methane domain input |
| Two-deep technical staff | Paired delivery in each pod; operational receivers at hypercare |

Microsoft roles

| Role | Responsibility | Indicative Hours |
| --- | --- | --- |
| Delivery Management Executive | Program oversight | 200 |
| Engagement Lead / Program Manager | Delivery accountability, governance cadence, change orders | 600 |
| Solution Architect | Architecture custody, ADR ratification, defensibility | 800 |
| Consulting Product Delivery Manager (CPdM) | Backlog discipline, sprint mechanics, capacity reporting | 480 |
| Data Engineer (lead + team) | OSDU + ADX + Fabric build, canonical contract | 1,400 |
| Data Platform Engineer | Landing zone, Fabric, FinOps Hub | 760 |
| AI Engineer | Foundry advisor, Azure ML forecasting, Content Safety | 900 |
| Edge / OT Engineer | AIO, historian adapter, diode validation | 720 |
| Security Engineer | Sentinel, Defender, STRIDE-lite, OIMS coordination | 640 |
| Reliability Engineer | DR, runbooks, SLO instrumentation | 580 |
| Joint team (paired delivery) | Co-build with XOM staff | 720 |
| Remaining specialist roles | Per WBS in OLR site Deliver tab; combined hours for these roles are capped at the remaining balance within the 14,500-hour total. | balance to 14,500 |

9 · Governance Framework

9.1 Governance Bodies

Executive Steering Committee — monthly. Outcomes, decisions, escalations.

Product Council — every two weeks. Backlog priority, capacity burn, change orders.

Architecture Review Board — weekly (or on ADR ratification). ADR custody, tradeoff transparency.

Cyber / OIMS Forum — weekly. Security risk burn-down.

9.2 Governance Functions

Strategy alignment, backlog prioritisation, problem resolution, decision authority, ADR ratification.

9.3 Communication Model

| Cadence | Forum | Output |
| --- | --- | --- |
| Daily | Pod stand-ups | Burn-down, blockers |
| Weekly | Architecture review, Cyber/OIMS forum | Decisions log entries |
| Every two weeks | Product Council | Capacity report, change orders |
| Each sprint | Sprint review + retrospective | Sprint completion report |
| Monthly | Executive Steering | Outcomes scorecard |
| Quarterly | Decision Pack readout | Concepts-tab "So What?" per C-suite lens |

10 · Delivery Execution (Sprint Model)

10.1 Sprint Activities

Sprint planning · Daily stand-ups · Implementation · Testing · Sprint review · Sprint retrospective.

10.2 Key Artifacts

Product backlog (mirrors OLR site Deliver tab — 60 leaf items).

Sprint backlog.

Sprint completion report.

Capacity burn-down chart.

Decision log (ADR proposals, ratifications, deferrals).

Proof graph evidence updates (OLR site Traceability tab).

11 · Testing and Quality Management

11.1 Testing Types

Functional — feature-level validation by the implementing pod.

System / integration — Microsoft, against the canonical event contract (ADR-05).

Non-functional — Microsoft, against the 17 NFRs and 7 SLOs published on the OLR site (see §16.3). Pass criteria are evidence-linked on the Traceability tab.

User validation / sprint review — Customer, against the work-product validation basis in §15.

DR drill (SLO-07) — Microsoft + Customer, 100% pass required for DEL-09.

Security attestation (STRIDE-lite + Cyber/OIMS sign-off) — Customer.

11.2 Responsibility Model

| Test type | Owner |
| --- | --- |
| Feature-level + system testing | Microsoft |
| Non-functional testing | Microsoft (Customer reviews) |
| UAT | Customer |
| Performance testing of OT systems | Customer |
| Security & OIMS attestation | Customer |

11.3 Defect Management

P1–P4 priority, S1–S4 severity. Defects enter the backlog; remediation is priority-driven per §6.

12 · Change Management

12.1 Principle

All changes to capacity, timeline, scope boundaries, fees, or contracted assumptions require a formally approved Change Order signed by authorised representatives of both parties.

12.2 Trigger Conditions

Capacity exhausted ahead of plan · Backlog expansion beyond capacity envelope · Timeline extension · Material change to roles or rate card · Architectural shift triggering ADR re-baseline (notably any move toward closed-loop OT control).

12.3 Process

Written change request from either party.

Impact analysis: cost, schedule, scope, risk.

Product Council review.

Approval or rejection within 3 business days of submission. If rejected and not resolved within a further 3 business days, the matter escalates to the Product Council and, if still unresolved within 5 business days, to the Executive Steering Committee for decision under §14.

Executed Change Order appended to this SOW.

Probe-set additions (for example, an eleventh hostile probe) do not require a Change Order; they are absorbed within the Defend-tab maintenance scope.

12.4 Change Order Log

The following Change Orders are incorporated into this v1.1 amendment. Subsequent CRs will be appended to this log under §12.3 process.

| CR | Title | Status | Effect on SOW |
| --- | --- | --- | --- |
| CR-01 | (reserved — number not used) | N/A | No change. |
| CR-02 | Expand site coverage from 1 pilot to 4 sites | Approved | §7 capacity model: 4 sites in scope; GA phase renamed "GA Hardening + Site Rollout"; site-specific rollout work added to MVP, GA, and Hypercare hour bands. |
| CR-03..CR-10 | (reserved — numbers not used in this amendment cycle) | N/A | No change. |
| CR-11 | Raise SOW capacity cap to absorb CR-02 | Approved | §7 total contracted capacity raised from 11,280h to 14,500h (+3,220h, +28.5%); §20.1 indicative fees updated proportionally. Magnitude subject to refined impact analysis at Mobilize exit; any further adjustment runs through §12.3. |
| CR-12..CR-13 | (reserved) | N/A | No change. |
| CR-14 | Raise NFR-14 cost guardrail to $4.8M Y1 | Approved | §16.3 NFR-14 updated; §20.2 Year-1 BOM envelope raised from $2.07M to $4.8M to accommodate 4-site footprint (additional AIO at 3 sites, expanded ExpressRoute / Firewall / OT-DMZ per site, additional Sentinel + Monitor ingest, Fabric F64 unchanged). FinOps Hub on Fabric (BOM-27) tracking against the revised envelope. |

Scope-narrowing note: This amendment also narrows the value-delivery scope to Pressure P1 (Volume-Returns-Emissions Triple Lock) and the OLR mechanism. P2 Pioneer-specific carve-out, P4 methane attribution, and P5 process-safety value delivery move out of scope per §5 items 11–14. The architectural foundation (all 9 ADRs, 28 components, 5 DET-01..05 OT-boundary controls, NFR-10/NFR-12 assurance) is retained — safety and audit remain as constraints, not value-delivery commitments.

13 · Risk and Issue Management

A RAID log (Risks, Actions, Problems, Decisions) is maintained continuously by the Microsoft Engagement Lead and reviewed at every Product Council. Top severity-weighted risks at SOW signing:

| Risk | Sev | Mitigation | Owner |
| --- | --- | --- | --- |
| RSK-WORK-01 — Data quality at edge ingest | H/LH | DQ gates at silver tier, Great Expectations, freshness SLO-04 | Data Engineer lead |
| RSK-WORK-02 — OSDU vendor delay | H/LM | Pre-engage at T-1, ECIF-funded, OSS OSDU in reserve | Engagement Lead |
| RSK-SEC-01 — Cyber/OIMS signoff delays | H/LM | Pre-circulate security model, weekly forum, STRIDE-lite | Security Engineer |
| RSK-CAPC-01 — AOAI PTU / Fabric F64 capacity | H/LM | Reservations placed at T-1, quotas filed early | Engagement Lead |
| RSK-PEOPLE-01 — Azure ML / Foundry talent scarce | H/LM | Two-deep on senior roles, GBB / FastTrack backfill | Engagement Lead |
| RSK-ADR-01 — One-way doors (ADR-01, ADR-09) | H/LL | Decisions attested at ratification, reversal cost documented | Solution Architect |
| RSK-COST-01 — FinOps overrun (NFR-14 budget breach) | H/M | FinOps Hub on Fabric (BOM-27); unit-economics dashboard reviewed bi-weekly at Product Council; tag-policy enforcement | Engagement Lead |
| RSK-COST-02 — Sentinel + Log Analytics ingest 2× over plan | M/M | 100 GB/day commit (BOM-24, BOM-30); rule-pack tuning; ingest filtering at DCRs | Security Engineer |
| RSK-WORK-04 — Pioneer-asset integration MV (D9) resolution delay | M/M | Defer to Y2 via scope gate (SCP-OUT-02); document MV trigger; WBS 6.1/6.2 carry contingency | Engagement Lead |
| RSK-REG-01 — Regulatory shift on methane reporting (SEC, EPA) | H/M | Narrative overlay in Y1; closure trigger documented (SCP-OUT-02) | Sustainability SME |

The full risk register (28 risks + NFRs combined view on the Traceability tab) is maintained live in the OLR Control Room Deliver tab.

Scope traps (items that can expand hours quickly if not actively managed):

Adding sites to the MVP pilot wave before DEL-08 green.

Allowing OT write-back conversations to re-open ADR-09 mid-program.

Methane attribution expanding from operated to non-operated assets (P4 → P3 drift).

Bespoke Power BI reports outside the canonical semantic layer.

Custom historian point mapping per site beyond the standard adapter pattern.

14 · Escalation Path

Pod / Feature team lead.

Microsoft Project / Program Manager (Engagement Lead).

Customer Product Owner.

Microsoft Delivery Management Executive.

Product Council.

Executive Steering Committee.

Escalation target: 1 business day per level; bypass permitted for safety-impacting problems.

15 · Work Products and Delivery Evidence

15.1 Typical Outputs

Architecture and design documents (ADRs ratified on the OLR site) · Product backlog · Sprint reports · Roadmaps and capacity burn-down · RUN-01..08 runbooks · Knowledge transfer artifacts · DR drill evidence · Security attestation pack · FinOps unit-economics dashboard · Hostile-probe console.

15.2 Named Work Products and Validation Basis

The following named work products provide delivery evidence and traceability to outcomes, constraints, or technical milestones. They are validated through sprint review and recorded evidence rather than separate formal acceptance unless expressly stated in a signed Change Order.

| ID | Deliverable | Outcome Supported | Acceptance Criteria | Phase |
| --- | --- | --- | --- | --- |
| D-01 | Landing zone (Entra, network, policy, monitoring) | O1, O8 | Policy assignments green; baseline scorecard ≥ 95%; DEL-04 attested | MVP |
| D-02 | OT ingest path — AIO + historian read adapter (one-way diode) at pilot site | O8 | Diode validation passed; ADR-09 attested by OIMS; evidence demonstrates all five OT-boundary controls (DET-01..05) are implemented and evidenced; NFR-10 (OT boundary integrity) verification pack signed; no write paths detected in a 7-day audit; DEL-05. | MVP |
| D-03 | Canonical event bus + bronze/silver/gold tiers (OSDU + ADX + Fabric) | O3, O5 | End-to-end event traceable from edge to gold; schema contract published; DEL-06 | MVP |
| D-04 | AI advisor MVP — Foundry RAG + Azure ML forecast + Content Safety | O3, O8 | 10 named queries return cited responses; Content Safety filters active; DEL-07 | MVP |
| D-05 | Engineer surface (Managed Grafana) + executive surface (Power BI) MVP | O3, O5 | Both surfaces read same semantic layer; KPI parity demonstrated; DEL-08 | MVP |
| D-06 | All nine ADRs ratified | All | Weighted criteria, alternatives, consequences attested on the Decide tab; Customer EA co-signature | MVP |
| D-07 | Active/Standby DR posture (ADR-07) — drill | O8 | SLO-07 100% pass in drill; DEL-09 | GA |
| D-08 | Cosmos Gremlin safety graph; PSE precursor flagging | O8 | DEFERRED — out of scope under CR (§5 item 11). P5 safety value-delivery removed from this SOW. NFR-10 OT-boundary assurance retained. | — |
| D-09 | Methane attribution at operated-asset boundary | O4 | DEFERRED — out of scope under CR (§5 item 12). P4 methane attribution removed from this SOW. | — |
| D-10 | FinOps Hub on Fabric — unit-economic dashboard | O1 | NFR-14 cost guardrail active; Y1 envelope tracking ±5%; DEL-12 | GA |
| D-11 | Security model attestation | All | STRIDE-lite reviewed; Cyber + OIMS sign-off; DEL-13 | GA |
| D-12 | RUN-01..08 runbooks authored and executed by XOM SRE | O8 | All eight runbooks executed by Customer staff, as evidenced at exit gate DEL-14. | GA |
| D-13 | Hostile-probe console (10 probes, ≥30 evidence references) | All | Defend-tab probes all linked to live evidence; freshness ≤ 14 days | Continuous |
| D-14 | Hypercare gate evidence pack (HG-01..06) | All | All six gates attested; DEL-15 | Hypercare |
| D-15 | Knowledge transfer — two-deep on senior roles | O8, O3 | Two-deep attestation across 7 named role groups; DEL-16 | Hypercare |
| D-16 | Operational handoff sign-off — DEL-17 | All | §17 evidence satisfied; signed by XOM Senior President Global Operations + ISD CTO | Hypercare |

15.3 Validation Model

Backlog items and named work products are reviewed in sprint review and validated against the criteria in §15.2 and the linked evidence.

Separate written acceptance is required only where a signed Change Order expressly designates a fixed-fee deliverable with formal acceptance criteria. Otherwise, absence of Customer objection in the applicable sprint review record confirms validation for tracking purposes and does not convert this engagement into fixed-price scope.

15.4 Work Package → Role → Hours

Hours are estimated by work package first, then allocated to roles. Both views are required and both are maintained live in the OLR site Deliver tab.

| Work Package | Key Activities | Primary Roles | Est. Hours | Notes / Dependencies |
| --- | --- | --- | --- | --- |
| WP-1 Foundation | Landing zone, identity, network, policy | Data Platform, Security, SA | 1,200 | ExpressRoute live; ECIF approved |
| WP-2 Edge / OT Ingest | AIO deployment, historian adapter, diode validation | Edge/OT, Security | 1,400 | OIMS forum cadence; vendor read-API cert |
| WP-3 Data Plane | OSDU + ADX + Fabric, canonical contract | Data Engineer team | 2,200 | OSDU vendor on-time |
| WP-4 AI Plane | Foundry RAG, Azure ML, Content Safety, Gremlin | AI Engineer, Data Engineer | 1,800 | AOAI PTU + Fabric F64 reserved |
| WP-5 Consumer Surfaces | Front Door, Grafana, Power BI | Data Platform, Reliability | 600 | Semantic layer published |
| WP-6 Resilience & Observability | Active/Standby DR, Monitor, FinOps Hub | Reliability, Data Platform | 900 | NCUS standby provisioned |
| WP-7 Security & Compliance | Sentinel, Defender, STRIDE-lite, OIMS | Security | 700 | Cyber weekly forum |
| WP-8 Sprint Mechanics & Governance | CPdM, EL, SA, decision log, ADRs | EL, CPdM, SA | 1,500 | — |
| WP-9 Knowledge Transfer & Hypercare | Runbooks, two-deep pairing, gate evidence | All pods + joint team | 980 | XOM staff in seats by GA |
| Total |  |  | 14,500 |  |

16 · Technical and Environment Requirements

16.1 Stack Patterns

Azure (core platform): hub-spoke + ExpressRoute; AKS + Karpenter; Container Apps; Functions Premium; APIM Premium.

Data: OSDU, ADX, Microsoft Fabric; Event Hubs Premium + Event Grid + Service Bus Premium.

AI: Azure AI Foundry + AOAI; Azure ML; AI Search; Cosmos DB for Gremlin; Azure AI Content Safety.

Edge: Azure IoT Operations on Arc-enabled Kubernetes.

Operate: Monitor + LA, Managed Grafana, Sentinel, Defender for Cloud, FinOps Hub on Fabric, Entra ID, Key Vault Premium + HSM, Power BI Premium, Front Door Premium.

DevOps: Azure DevOps / GitHub Enterprise — Customer-selected.

16.2 Environment Model

| Environment | Purpose | Ownership |
| --- | --- | --- |
| Dev | Pod-level development | Customer-owned; Microsoft granted access |
| Test / Pre-prod | Integration, NFR, DR drill | Customer-owned; Microsoft granted access |
| Production (SCUS) | Active primary | Customer-owned |
| Production (NCUS) | Standby | Customer-owned |
| Site / OT zone | Pilot well-pad ingest | Customer-owned; Microsoft granted scoped access via OT-DMZ |

16.3 Non-Functional Requirements (sourced from OLR site Traceability tab)

The following 17 NFRs and 7 SLOs are the authoritative non-functional reference basis. Targets and measurement methods are maintained in the Schedule H snapshot and related artifacts; this SOW provides that Microsoft plans to deliver evidence against each within contracted capacity and subject to backlog prioritization. These references do not create a standalone SLA or warranty under this SOW.

Non-Functional Requirements (NFR-01..17)

| ID | Requirement | Tied to |
| --- | --- | --- |
| NFR-01 | Advisor end-to-end latency | C-12, C-13, SLO-01 |
| NFR-02 | Event → engineer-dashboard latency | C-06, C-22, SLO-02 |
| NFR-03 | Ingest throughput (sustained) | C-06, C-10 |
| NFR-04 | Advisor availability | C-12, ADR-07 |
| NFR-05 | Ingest availability | C-06, ADR-07 |
| NFR-06 | RPO (hot tier) | ADR-07, SLO-07 |
| NFR-07 | RPO (cold tier) | ADR-07 |
| NFR-08 | RTO composite | ADR-07, SLO-07 |
| NFR-09 | Data residency (US regions only) | ADR-02 |
| NFR-10 | OT boundary integrity | ADR-09, DET-01..05 |
| NFR-11 | Identity hygiene | ADR-01, C-27 |
| NFR-12 | Audit completeness | C-21, C-23 |
| NFR-13 | Privacy / DLP | C-16, C-26-equivalent |
| NFR-14 | Cost guardrail — revised under CR-14 to $4.8M Y1 envelope (was $2.07M; +$2.73M to absorb 4-site footprint per CR-02) | C-26 FinOps Hub, BOM envelope |
| NFR-15 | Supportability / KT (hypercare exit) | DEL-15..17, HG-01..06 |
| NFR-16 | Accessibility (engineer surface) | C-22 |
| NFR-17 | Sustainability | Tenant-level reporting |

Service Level Objectives (SLO-01..07)

| ID | Objective | Owner |
| --- | --- | --- |
| SLO-01 | Advisor latency budget | AI Engineer |
| SLO-02 | Event-to-dashboard latency budget | Data Platform |
| SLO-03 | Advisor availability budget | Reliability Engineer |
| SLO-04 | Data freshness at silver/gold | Data Engineer |
| SLO-05 | Ingest availability budget | Edge / OT Engineer |
| SLO-06 | Surface availability (Grafana + Power BI) | Reliability Engineer |
| SLO-07 | DR composite (RPO + RTO) | Reliability Engineer |

Error-budget policies and burn-rate alerts for SLO-01..07 are delivered under WBS 4.5 and exit-attested at HG-04.

16.4 OT-Boundary Controls (DET-01..05)

The one-way OT/IT contract (ADR-09) is enforced by five independent, defense-in-depth controls. All five must be live and continuously evidenced; failure of any single control is a Sev-1 escalation under §14.

| ID | Control | Mechanism | Evidence |
| --- | --- | --- | --- |
| DET-01 | ADR-09 architectural prohibition | Platform never writes to DCS / SCADA / SIS; never initiates shutdowns; never changes setpoints | ADR-09 attested by OIMS |
| DET-02 | Azure Firewall Premium rule-as-code | Deny cloud → OT subnet egress at the network plane; rules versioned in IaC | C-03 NFR-10 verification pack |
| DET-03 | AKS NetworkPolicy guardrail | Pod-level NetworkPolicy blocks any workload egress routing toward OT/DCS subnets | C-17 NFR-10 verification pack |
| DET-04 | Sentinel anomalous-egress detection | SIEM rule fires on any flow whose destination matches OT subnet space; notifies SOC and operations as soon as practicable, target within 5 minutes | C-23 NFR-10 + NFR-12 audit |
| DET-05 | Quarterly OT red-team drill | Adversarial test attempts cloud → OT write path each quarter; failure to block is Sev-1 to safety leadership | DR-04 drill cadence |

17 · Customer Responsibilities

ExxonMobil will provide and manage the following. Failure to meet these may impact capacity burn and timeline.

Provide:

Access to in-scope Azure subscriptions, OT perimeter network environments, and pilot site systems.

SMEs in drilling, completions, reliability, methane, subsurface, and finance.

Documentation: existing architecture, historian point lists, data catalogues, security baselines.

UAT execution against §15.2 acceptance criteria within agreed windows.

Two-deep staffing across the seven named role groups by MVP start (T+3).

AOAI PTU and Fabric F64 reservations at T-1 (RSK-CAPC-01 mitigation).

ExpressRoute circuits to Texas primary region commissioned within Mobilize.

OIMS attestation on ADR-09 prior to DEL-05.

Customer-procured third-party software: PI / AVEVA, OSDU vendor.

Manage:

External vendor dependencies (PI / AVEVA, OSDU vendor).

Organisational readiness, end-user communications, and change management.

All third-party interactions and contracts.

Security and compliance reviews on Customer cadence.

Site safety, badging, and physical access at pilot wells.

Engagement-level completion criteria for DEL-17 (Operational Handoff):

Three P1 incident simulations or chaos drills using the runbooks, or three real P1 incidents owned by ExxonMobil SRE, whichever comes first, as evidenced at exit gate DEL-17. This evidence is for DEL-17 only and does not create an ongoing SLA or warranty.

All eight RUN-01..08 runbooks executed by ExxonMobil staff.

DR drill SLO-07 at 100% pass.

Error-budget policy attested by ExxonMobil SRE leadership.

FinOps Y1 envelope held within ±5%.

Two-deep knowledge-transfer attestation across the seven named role groups.

Signed handoff: XOM Senior Vice President Global Operations + ISD CTO.

18 · Assumptions

The following assumptions make the estimate true. Material deviation triggers §12 (Change Management).

Customer two-deep staffing is in place at MVP start (T+3).

ExpressRoute circuits are commissioned within Mobilize.

AOAI PTU and Fabric F64 reservations are placed at T-1.

ECIF approval funds Mobilize and the pilot AIO deployment.

Cyber and OIMS forums meet weekly throughout MVP and GA.

Customer retains decision authority on ADR ratifications; Microsoft retains authorship and tradeoff transparency.

Pioneer-acreage data residency and operatorship model is stable through GA.

Delivery is continuous — no extended breaks; statutory holidays planned in capacity.

Delivery is remote / hybrid, with on-site presence as needed for pilot ingest and DR drill.

Compliance and mandatory training time is included in capacity at 5%.

Agile variability is acknowledged: scope may shift sprint-to-sprint within capacity.

Tooling readiness: Azure DevOps / GitHub Enterprise, Defender, Sentinel licences and access provisioned by Mobilize exit.

19 · Program Completion Criteria

The Engagement completes upon the earliest of:

Backlog complete — DEL-17 evidence (§17) satisfied and signed.

Capacity consumed — 14,500 hours expended without DEL-17 signature. The parties will document the state of in-flight work products, handover materials, and any remaining backlog, and any additional work requires a signed Change Order under §12.

Timeline expires — 18 months from Effective Date without extension.

Contract terminated — under the MCSA termination provisions.

Sections §15 (surviving deliverables), §16 (Customer environments), and the underlying MCSA Confidentiality / IP / Data Protection terms survive termination.

20 · Pricing & Commercial Terms

(Provided as a commercial schedule appended to the EX3-mandated structure above.)

20.1 Professional Services Fees — Capacity-Based

Microsoft will perform the Services on a time-and-materials engagement with a fixed-capacity cap basis at the agreed blended rate. The capacity below is the commercial cap; consumption is reported each sprint.

| Phase | Capacity (hrs) | Indicative Fees (USD) |
| --- | --- | --- |
| MVP Build | 5,400 | $1.54M – $1.89M |
| GA Hardening + Site Rollout (4 sites) | 7,200 | $2.05M – $2.52M |
| Hypercare & Transition | 1,900 | $0.54M – $0.67M |
| Total Professional Services (revised under CR-11) | 14,500 | $4.13M – $5.08M |

Final rate card and ECIF offset are confirmed in Schedule A prior to signature.

20.2 Azure Platform & Licences (Customer-paid, out of scope per §5)

Year-1 Bill of Materials envelope revised under CR-14 to $4.8M (was $2.07M) to accommodate the 4-site footprint per CR-02 — additional AIO deployments, OT perimeter network provisioning, ExpressRoute / Firewall scale-out, and expanded Sentinel + Monitor ingest. Itemised in the OLR Control Room System tab (Schedule B, re-baselined). Customer contracts directly for all Azure consumption, AOAI PTU reservations, Fabric F64, Power BI Premium, and third-party software. NFR-14 cost guardrail set to the revised envelope; FinOps Hub (C-26 / BOM-27) tracks against it.

20.3 Expenses

Pre-approved, reasonable travel and incidentals at cost, capped at 8% of professional services fees.

20.4 Invoicing

Monthly in arrears, net 30 days, against actual hours and expenses.

21 · Signatures

Microsoft Corporation — Industry Solutions Delivery

Name: ______________________________   Title: ______________________________

Signature: ___________________________   Date: ______________________________

Exxon Mobil Corporation

Name: ______________________________   Title: ______________________________

Signature: ___________________________   Date: ______________________________

22 · Appendices and Supporting Material

Schedule A — Detailed Fee Schedule and Rate Card (attached at signature).

Schedule B — Year-1 Bill of Materials (mirrors OLR Control Room System tab).

Schedule C — Full WBS, 60 leaf items (mirrors Deliver tab).

Schedule D — Full Risk Register and RAID log baseline (mirrors Deliver tab).

Schedule E — ADR Register, 9 ADRs with weighted criteria (mirrors Decide tab).

Schedule F — Hostile-Probe Console baseline, 10 probes + evidence (mirrors Defend tab).

Schedule G — Glossary and Acronyms (below).

Schedule H — Reference Architecture Diagrams (mirrors Concepts and System tabs).

Schedule I — Sprint-zero Backlog Snapshot.

Schedules B–F and H are reflected in the OLR Control Room reference site. The site state at SOW Effective Date is captured in an executed PDF snapshot attached to this SOW, and that snapshot is the binding technical baseline.

Schedule G — Glossary and Acronyms

| Term | Definition |
| --- | --- |
| ADR | Architecture Decision Record |
| AIO | Azure IoT Operations |
| AKS | Azure Kubernetes Service |
| AOAI | Azure OpenAI |
| BOM | Bill of Materials |
| CPdM | Consulting Product Delivery Manager |
| DCS | Distributed Control System |
| DEL | Delivery gate |
| DET | Detection / boundary-enforcement control (OT) |
| DR | Disaster Recovery |
| ECIF | Enterprise Commercial Investment Funds |
| HG | Hypercare Gate |
| MCSA | Microsoft Consulting Services Agreement |
| NCUS | North Central US (Azure region) |
| NFR | Non-Functional Requirement |
| OIMS | Operations Integrity Management System |
| OLR | Operational Learning Rate |
| OSDU | Open Subsurface Data Universe |
| OT | Operational Technology |
| PSE | Process-Safety Event |
| PTU | Provisioned Throughput Unit (Azure OpenAI) |
| RAID | Risks, Actions, Problems, Decisions |
| RUN | Run Operations procedure (runbook) |
| SCADA | Supervisory Control and Data Acquisition |
| SCUS | South Central US (Azure region) |
| SIS | Safety Instrumented System |
| SLO | Service Level Objective |
| SRE | Site Reliability Engineering |
| UAT | User Acceptance Testing |
| WBS | Work Breakdown Structure |

EX3 Compliance Map

| EX3 Requirement | Location in this SOW |
| --- | --- |
| §1 Document Control | §1 |
| §2 Introduction (Context · Purpose · Engagement Model) | §2.1, §2.2, §2.3 |
| §3 Objectives and Scope (Objectives + non-guarantee · Value Themes · Scope Model) | §3.1, §3.2, §3.3 |
| §4 Structured Scope (Epics / Workstreams) | §4 |
| §5 Out of Scope | §5 |
| §6 Delivery Approach | §6 |
| §7 Timeline and Capacity Model | §7 |
| §8 Organization and Roles | §8 |
| §9 Governance Framework | §9 |
| §10 Delivery Execution (Sprint Model) | §10 |
| §11 Testing and Quality Management | §11 |
| §12 Change Management | §12 |
| §13 Risk and Issue Management (RAID) | §13 |
| §14 Escalation Path | §14 |
| §15 Work Products and Delivery Evidence (+ validation, + hours-by-role AND hours-by-work-package) | §15.1–§15.4 |
| §16 Technical and Environment Requirements | §16 |
| §17 Customer Responsibilities | §17 |
| §18 Assumptions | §18 |
| §19 Program / Project Completion Criteria | §19 |
| §22 Appendices and Supporting Material | §22 |
| Microsoft Paper checklist — customer language, defined acronyms, scope traps | §2.3, §13 |
| Estimation drivers explicit | §7 (drivers), §15.4 (WBS) |
| Hours by role AND by work package | §8.2 + §15.4 |